XXVI DEVELOPMENT PARTNERS COORDINATION GROUP MEETING
Held on Wednesday, 2 November 2005, at 10h00
in the MINECOFIN Basement Conference Room
Kigali, Rwanda

MEETING MINUTES

Annex I: Follow-up matrix
Annex II: List of attendees
ANNEX III: Presentation on Development of the Aid policy
ANNEX IV: Public Sector reform progress

1. Agenda Item #1: Review and Adoption of 30 September 2005 DPCG Minutes

  - Being their first DPCG Meeting, SG MINECOFIN John Rwangombwa and UN RR/RC, Moustapha Soumaré, introduced themselves.

  - The Co-Chair, UN RR/RC, reviewed the 30 September 2005 DPCG minutes. The minutes were adopted with no changes.

  - The Chair, SG MINECOFIN, reviewed the Agenda for the DPCG Meeting.

    - Update on Public Sector Reform and proposed schedule for next DPCG Meetings were added as AOB.

- Agenda Item #2: Development of the Government of Rwanda Aid Policy Document

(See Annex III: presentation by Jean Jacques Nyirubutama)

  - The following discussion stemmed from the presentation on the APD.

  - A development partner requested more detail on the objective of the policy. It was suggested that the policy should include provisions on project support since many partners have budget and legal constraints. It was also mentioned that the policy should call for further actions in terms of a Joint Assistance Strategy which will serve as a link between donors and government.

    - The SG stated that the GOR is defining its preferred aid modalities leaving margin for project support to remain a valid option, yet subject to some specific conditions that will be defined by the APD .

    - The UN RR/RC mentioned that a JAS is very important. The idea is to have a UN Joint Strategy which responds to PRSP II/EDPRS.

    - EFU Director stated that it is impossible to fix a timetable for the elaboration of a JAS. Next year, all parties involved should arrive to a consensus and then an execution phase.  During this phase, the GOR will proceed to evaluations to monitor the advancement of the document..

    - According to a Development Partner the APD must be the fruit of discussion. The APD must be an open and action orientated policy.

  - The EC welcomes the paper. It will shortly arrive to its conclusions regarding the paper and forward these to its HQ. The initial feeling is very positive. Generally, the EC is promoting close coordination between its program and its member states. What is being done in Rwanda has gone beyond this. The EC country office is reporting to Brussels that in Rwanda, technical assistance includes the donor community and government.

  - It was suggested that the policy address the challenges faced in aid. More than 70% of aid is going to governance. On the ground, there is health infrastructure, however, the human capital is lacking. How can aid be redirected to increase its efficiency? How can aid help the private sector develop agriculture business? How can aid foster industry in order to generate and increase income? These challenges should be addressed in the APD. Finally, donors and ministries should improve negotiations: What role can MINECOFIN play to increase time efficiency and decrease bureaucracy?

    - The SG responded that the APD will be linked to the EDPRS. We are currently in phase of evaluating the PRSPI and developing PRSPII/EDPRS. The EDPRS will focus more on growth sectors and not only social areas.. The APD must address these issues to reduce transaction costs in aid management and promote alignment to the priorities that are defined by the national plans including the future EDPRS. The GOR is also developing a long term investment plan to determine the role of private sector and its sources of financing.

    - The EFU Director stated that negotiations continue to cause problems since these lead to few results. Ministries often show up with shopping lists. The APD will ensure that MINECOFIN is the planning house for all negotiations with donors. Unfortunately, development partners continue to negotiate directly with line ministries.

  - A development partner stated that donors are also confronted by parallel governmental structures, such as national commissions. It was asked whether these would be covered by the APD.

    - The SG responded that the APD covers all government institutions, including commissions. The APD is to promote alignment for all sectors.

    - Moreover, it was agreed that all DPs submit their feedback on the APD Consultation Paper by the 18th of November, in order to get comments prior to the workshop on the APD being held on the 22nd of November with line ministries.

- Agenda Item #3a: Progress on Design of the Rwanda Development Assistance Database

  - Didier Gakuba gave an update on the Development Assistant Database.

    - Last week we had a visit of a specialist from Synergy International for some consultations with the government and Donors regarding the content of the template for data collection and the kind of reports we need. Findings from the consultations mission were

- Clear definition for pledges, commitments, and disbursements, from donors

- Encourage compatibility with SmartGov

- Quality control should be maintained

- Should track projects planned-ongoing-completed

- Possibility of deploying “mini-DAD” to administrative territories

    - Next steps

- Development of DAD-Rwanda prototype begins on Monday, October 31st with goal of having prototype available for DPM (1 December 2005)

- Continue to work with Government of Rwanda and key officials to obtain budget classifications and definitions, desired indicators on behalf of government, and new geographic classifications based on Administrative Reforms

- Send data collected through IDB to Synergy International

- Synergy sends data form template to EFU/ACU for review

- During first two weeks of November, final data entry form and classifications are decided by the Government and made available to Synergy International Systems

- In parallel, EFU/ACU drafts FAQs and letter of instruction to donors on data flow definitions, roles, and responsibilities.  Synergy sends template for support.

- Synergy will finalize an online prototype posted on their Web server for feedback at least one week prior to DPM

- Synergy will implement changes to the prototype and make available final prototype for showcase at DPM by UNDP/EFU.

  - The following discussion stemmed from the update on DAD.

    - A development partners asked if the DAD system will allow for more comprehensive and active data for sectors.

      - The EFU Director responded that the system will allow for overview of sectors. In developing DAD, MINECOFIN needs development partners and the GOR to contribute all necessary information. All comments will help enrich DAD as it is being developed by consultants.

      - ACU Head stated that a reporting template will be provided soon with instructions on definitions and classifications to get feedback from development partners. Deadlines will be sent for provision of feedback in order to have the DAD prototype  demonstrated at DPM. The finalized DAD will be ready by January 2006.

    - A DP asked what would be the reporting frequency required by the system. What has become of Interim Database?

      - EFU Director responded that as in previous years, MINECOFIN is seeking to compile a report detailing official development assistance to Rwanda. This year, the External Finance Unit is responsible for the production of this report. The report is intended to provide an overview of all flows of assistance to Rwanda, both in the current year, and predictions for the next two financial years. This information plays an essential role in the planning process, as well as providing evidence that may be of use in the evaluation of aid effectiveness.

      - Whilst it is hoped that the forthcoming DAD will make donor reporting much easier and clearer in the near future, an interim database is being constructed by EFU for the capture and reporting of this year’s data. We accept that no such report will ever be comprehensive and 100% accurate. This year, the decision was made to improve the quality rather than quantity of the report, and to focus on the collection of data from multilateral and bilateral development agencies, thus avoiding the double counting of funds originating from these agencies and being channeled through NGOs.

      - At present, most of the large donors have been contacted by email and invited to provide data on development assistance via an online form. Whilst some form of response has now been received from most of these partners, we are currently faced with a range of problems that will have an adverse affect on the quality of this year’s Report and any subsequent analyses or plans based on it.

      - Planned ODA for 2005 recorded in the database totals approximately 325 million USD. This is significantly lower than expected, indicating large gaps in the coverage of our data. The main problems identified are as follows:

- Listings provided are incomplete, with some agencies giving details of only one project when they are known to be financing many more.

- Inadequate descriptions are offered, making it impossible to verify data against other sources.

- Data provided is not always the most recent data available.

- Category fields left blank, making it impossible for us to analyze, for example, the sectors or geographical areas in which assistance is being provided, as well as the modalities of such assistance.

- Lack of disbursement data, with many agencies providing only data on planned assistance for 2004 and 2005.

- Lack of predicted / planned assistance data for future years, rendering any attempt to plan ahead very difficult.

- Basic errors in reporting arising from arithmetic mistakes, failure to keep accurate records etc. ( This is may be due to the fact that 100% of pledges  have not been disbursed or expenses have been higher than the initial pledges) if  so then it is not a problem of data collection.

- Non-response from some donors

- Failure of partners to provide data in format requested by EFU, making integration into the database or comparison with other data almost impossible.

      - EFU realizes that a small number of partners may not have received invitations to submit assistance data, and is taking steps to contact those agencies and obtain accurate data.

      - Urgent action required

- Those donors that have provided little or no data are invited to provide this as a matter of urgency.

- Donors that have provided data will be sent a report of all data held for them electronically this week. They are kindly requested to check this for accuracy and supplement this data with any additional data that may be held.

- Where precise figures are not available (particularly for future financing), estimated figures should be provided. Figures provided are by no means binding, and as such approximate figures are better than no figures at all. The importance of this data collection exercise cannot be stressed enough. We appreciate the help of all partners.

      - The SG stated that the problem is getting all the information for the database to be functional and useful. There is also a direct link between this database and the financial accounting systems of government.

      - The ACU Head stated that IDB data is currently being compiled and will be shared with development partners. The IDB will end at one point since it is intended as an interim project; its life will finish with the DPM and when DAD will be functional.

      - ACU member stated that the data given for the IDB will be integrated into DAD. DPs will not have to resubmit their information.

- Agenda Item #3b: Progress on DPM Preparations

  - The Cabinet met last week and confirmed the dates (1, 2 December) and objectives of the 2005 DPM. All invitation letters have been sent to all participants by the DPM Secretariat. The deadline for receiving the registration forms for confirmation is Nov 4th, 2 days after the DPCG.  Request that all donors confirm their participation and the participation of one or more headquarters representatives.  If confirmation and travel dates are not received prior to November 11th, the DPM secretariat cannot assure a reservation at the Intercontinental Hotel for participants traveling from abroad.

    - All documents relating to the DPM will be posted on the Development Partners website as soon as they are received, and will be accessible in both French and English.  The detailed agenda will be distributed through the website prior to the next DPCG.  The website address is: www.developmentpartners.rw/dpm/2005.html

    - MINECOFIN has assembled an organization committee with other Ministries and is finalizing arrangements for the DPM.

    - For any further information, invited participants can contact the DPM secretariat, comprised of the External Finance Unit and Aid Coordination Unit, by email at dpm@developmentpartners.rw

- Agenda Item #4: Announcements

  - EFU/ACU Integration

    - Following recommendation from the DPCG retreat held in February, MINECOFIN found suitable space for integration.  As of 2 weeks ago, both units have integrated.  Units have started to match capacities.

  - DPCG Newsletter has been launched by the ACU

    - The Newsletter has been distributed, which provides updates on highlights and main developments of harmonization and alignment

  - DPCG Meetings are scheduled for:

- DPCG Meeting – 24 November 2005

- DPM – 1 and 2 December 2005

- DPCG Meeting – 12 January 2006

- DPCG Retreat – 9 and 10 February 2006

  - EC Meetings

    - 2 November 2005 at 1500 to discuss trust fund for PFM.

    - Debriefing by IMF visiting mission at EC on 8 November 2005 at 1430.

- Agenda Item #: AOB

(See Annex III: presentation by SG Vincent Karega)

  - The following discussion stemmed from the presentation on public sector reform.

    - A development partner stated concerns regarding capacity building. We are discussing the annual portfolio with CEPEX:

- We are meeting international standards of procurement.

- We should make sure that procurement standards are followed. That is on of the big problems in that donors are not supporting procurement issues.

- In other countries, ICT is used to enhance capacities, we can combine with this.

    - Another development partner stated that there is a need for an attitude change, a shifting to local government and an upgrade of the level of knowledge in the ministries. More policy thinking requires more expertise. Ministries will work more on planning and way forward rather than service delivery.

In his closing remarks, the UN RC stated that it is clear that the Aid Policy Document will be an important document.  However, one issue needs to be clarified: Sector approach – How can we see the way sector groups operationalize and become more efficient.

Secretary General
Ministry of Finance and Economic Planning
Government of the Republic of Rwanda
Co-Chair of the Development Partners Coordination Group

UN Resident Coordinator / Resident Representative
United Nations Development Programme
Kigali, Rwanda
Co-Chair of the Development Partners Coordination Group

| Follow-Up Action(s) | Responsibility | Required Coordination | Action to be complete by: | Status |
| --- | --- | --- | --- | --- |
| Development partners to submit feedback for the APD | DPs | EFU | November 18 |  |
| Reporting template for feedback on DAD to DPs | ACU | EFU | November 10 |  |
| Development partners to provide feedback on DAD using template | DPs | EFU/ACU | November 15 |  |
| DAD prototype to be completed | Synergy International/EFU | ACU | December 1 |  |
| DAD to be finalized | Synergy International/EFU | ACU | January 2006 |  |
| Development partners which have not done so to provide all appropriate data for the IDB | DPs | EFU/ACU | ASAP |  |
| All registration forms for the DPM to be submitted | All DPM Participants | ACU - EFU | November 4 |  |
| All confirmation and travel dates for DPM to be submitted | Out of country participants | Country Offices | November 11 |  |

(by Organization)

|  | Full Name | Job Title | Organization |
| --- | --- | --- | --- |
| 1 | Michael Bayingana | Economist | External Finance Unit - MINECOFIN |
| 2 | Danila Boneva | Program Specialist | UNRCO - United Nations Resident Coordinator's Office |
| 3 | Dirk Brems | Cooperation Attaché | Belgian Embassy |
| 4 | Paul Farran | JPC | UNRCO - United Nations Resident Coordinator's Office |
| 5 | Sandra Diesel | Program Manager | SIDA |
| 6 | Mbaye Diouf | Regional Director | UNECA |
| 7 | Liz Drake | Rural Sector Anchor | World Bank |
| 8 | Julie Fournier | Second Secretary | Canadian Embassy |
| 9 | Didier Gakuba | ICT Specialist | EFU |
| 10 | Laurent Gashugi | Assistant Representative | FOA |
| 11 | H.E. Marc Gedopt | Ambassador | Belgian Embassy |
| 12 | Thedore Hakizimana | Project Coordinator | MINECOFIN |
| 13 | Dirk Heuts | Cooperation Counselor | Belgian Embassy |
| 14 | Vincent Karega | SG MIFOTRA | MIFOTRA |
| 15 | John Kayemba | Economist | IMF |
| 16 | Bintou Keita | Representative | UNICEF |
| 17 | Paul Lambers | Delco/BTC/MINECOFIN | BTC |
| 18 | Claudia Lormann-Nsengiyumva | Country Director | DED-German Development Service |
| 19 | Xavier Mbarubukeye | Acting SG | MINECOFIN |
| 20 | Kevin Mullally | Mission Director | USAID |
| 21 | Doreca Musenga | Administrative Assistant | UNRCO - United Nations Resident Coordinator's Office |
| 22 | Baloko Nakala | Director ICT | MININFRA |
| 23 | Alain Noudehou | Resident Representative a.i. and Programme Director | UNDP - United Nations Development Programme |
| 24 | Jean Jacques Nyirubutama | Director | EFU |
| 25 | Robin Ogilvy | ODI Fellow | EFU |
| 26 | Masayoshi Ono | Japanese ODA Advisor | JICA - Japan International Cooperation Agency |
| 27 | Kareem Oweiss | Program Assistant | UNRCO - United Nations Resident Coordinator's Office |
| 28 | Vijay Pillai | Deputy Head (Programmes) | DFID |
| 29 | Gianluca Rampolla del Tindaro | Head of Aid Coordination Unit | UNRCO - United Nations Resident Coordinator's Office |
| 30 | Dereck Rusagara | ICT Associate, Aid Coordination Unit | UNRCO - United Nations Resident Coordinator's Office |
| 31 | John Bosco Ruzibuka | Assistant Representative | UNFPA |
| 32 | John Rwangombwa | Secretary General | MINECOFIN |
| 33 | Moustapha Soumaré | UN RR/RC | UNDP |
| 34 | Iwao Tatsumi | Resident Representative | JICA |
| 35 | Gertjan Tempelman | Deputy Chief of Mission and Head of Development Cooperation | Royal Netherlands Embassy |
| 36 | Christophe Tocco | Supervisory Program Officer | USAID |
| 37 | Mohamed A. Touré | Country Manager | WB |
| 38 | Christine Umutoni | Head of Justice, HIV/AIDS and Gender Unit | UNDP |
| 39 | Dirk van Hove | Country Coordinator | UNAIDS |
| 40 | Hans van Schroeder | Deputy Chief of Mission and Head of Cooperation | German Embassy |
| 41 | Mathias Weingert | Country Director | SDC |
| 42 | Petra Windisch | Country Director | GTZ |